Fund Berkeley's Capital by Risk — Not by Silo

A proposal to adopt a transparent capital-prioritization framework for the FY2028 budget cycle

The problem

On June 16, the City Council was presented a five-year Capital Improvement Program listing 149 projects and roughly $2.1 billion in unfunded capital need — organized by department, with no visible ranking of which needs come first or why. Years 3–5 carry no named projects at all. In short: a wish list, not a priority list.

Why it matters

Berkeley owns about $609M of depreciated capital but needs ~$2.1B to bring it to standard — a 3-to-1 gap — while carrying ~$807M in pension and OPEB debt and a negative unrestricted net position. With dollars this scarce, the order in which we fund matters as much as the total. Yet the City has no published method for setting that order. This is out of step with GFOA best practice, which calls for explicit, criteria-based scoring of every capital request.

The evidence

• Only one asset class carries a legal mandate: the sanitary sewer, under a federal consent decree (≥4.2 mi/yr to 2036). Everything else is discretionary — so the order is a choice the City is making invisibly.

• Streets sit at PCI 56 (“At Risk,” below the regional 67) with a $250M+ backlog; the adopted plan admits it will not reach “good.”

• Stormwater has a $208M need funded by ~$2.3M/year — from a fee not raised since the early 1990s.

• The Marina ($131M unfunded, failing docks and pilings) has run a structural deficit for 15+ years.

The ask

Adopt and publish a capital-prioritization rubric — score every project 0–5 on nine weighted criteria (legal mandate, health & safety, asset condition, cost of deferral, service preservation, equity, funding leverage, coordination, climate resilience) and rank by weighted total. This is process reform, not a list of cuts: it tells residents how decisions are made, and lets the numbers — not the loudest department — set the order.

What it produces — the ranked list the CIP didn't show

| # | Asset class | Governing mandate | Score | Tier |
| --- | --- | --- | --- | --- |
| 1 | Sanitary sewer | Federal consent decree | 378 | Tier 1 — Must-Do |
| 2 | Stormwater / watershed | MRP permit | 368 | Tier 2 — High |
| 3 | Streets / pavement | None (Vision Zero) | 336 | Tier 2 — High |
| 4 | Sidewalks | ADA (partial) | 334 | Tier 2 — High |
| 5 | Facilities / Civic Center | Seismic life-safety | 328 | Tier 2 — High |
| 6 | Marina / Waterfront | None (enterprise) | 297 | Tier 3 — Medium |

Illustrative: the BeTH rubric applied to Berkeley's asset classes. Mandated work (consent decree, ADA, seismic) is funded first by rule; the weighted score orders the discretionary remainder. Lowest-ranked: urban forest (188) and streetlights (206).

Berkeley Transparency Hub (BeTH)  ·  Sources: Berkeley FY27–31 CIP (Item 40c), 5-Year Paving Plan FY24-28, EPA Consent Decree, 2012 Watershed Plan, Marina Fund Update (2025), ACFR FY2024, GFOA Capital Planning best practice.